## Sheet1
Implementation Plan for Climate Change Strategy and Local Action Plan
No. | Strategy/action | Timing | Priority | Timeline | Responsibility | Indicator | Tasks | Progress and comments | Traffic light
1 | Identify where climate change knowledge gaps are and where further investigation is needed. | Medium term | Low | 2024/25 - 2026/27 | Strategic Planning | Gaps identified and investigation undertaken | Gap analysis of climate change knowledge | Local impacts of climate change identified and mitigation/adaptation measures considered. The science of climate change and knowledge gaps is beyond the capacity of local government.
2 | Incorporate global, national, regional and local, scientifically based research for predictive modelling, scenario planning, identification of knowledge gaps and information dissemination. | Long term | Key | 2027/28 - 2029/30 | Governance | Research incorporated into Shire procedures | Incorporate climate change research and knowledge into Shire procedures | At the June 2022 Ordinary Council Meeting, Council noted the Shire's forward program for policy review. As part of routine policy review climate change will be considered in making a recommendations for Council on relevant policies.
3 | Incorporate relevant up to date risk assessment information. | Short term | Key | 2022/23 - 2023/24 | Governance | Risk assessment incorporates climate change | Incorporate climate change into risk assessments | As part of the Shire's Risk Maturity Journey, a category of 'Environmental / Heritage' is incorporated in risk assessments. The risk appetite for this risk is 'low' meaning that the Shire is sensitive to risks associated with protection of the environment, including from climate change.
4 | Identify suitable carbon trading schemes and participate in their development. | Long term | Low | 2027/28 - 2029/30 | Natural Reserves Coordinator | Schemes identified and participation investigated | Identify carbon trading schemes | No action - no current resources
[7 empty] | Investigate participation in schemes | No action - no current resources
5 | Promote and incorporate lifestyle/behavioural change in residential, rural, commercial and industrial sectors including continuing to reduce and measure GHG emissions. | Ongoing | High | 2022/23 - 2029/30 | Switch your thinking, Communications | Number of promotions undertaken, measurement and reduction of GHG emissions | Promote lifestyle/behavioural change | SYT's main target audiences are local community members and businesses, so engagement with industrial sectors is limited to the Switched On Business award and green businesses e-news. Some reach on semi-rural audiences but not much rural. Switch present a range of sustainability workshops to the community. The workshops have been poorly attended, particularly in SJ, despite promotion efforts. Behaviour change is promoted mostly through workshops, Switched on Business awards, Rewards for Residents program, and communications platforms. SYT also distributes printed sustainability resources. This behaviour change is very difficult to accurately measure. The Shire promotes Switch Your Thinking programs and initiatives via social media and enewsletters.
[7 empty] | Measure and reduce GHG emissions | There is no direct reduction or measurement of the GHG emissions of the SJ community. The online tool snapshotclimate.com.au assists LGAs to estimate their community emissions profile. SJ can work with Ironbark Sustainability and BZE to further track this for a fee. SJ has a total estimated municipal emissions of 526,000 t CO2-e (2019-20) and this is largely made up of transport (60%) and residential electricity (22%). Much more can be done by the Shire to improve residential home efficiency and promote active transport. SYT are currently working together with Health and Building Services to roll out a home energy efficiency trial in SJ.
6 | Promote and educate the community on the importance of local food production, good public transport, the slow food movement, food miles and resource recycling. | Short term | Key | 2022/23 - 2023/24 | Switch your thinking, Communications | Number of promotions undertaken | Promote local food production | Can be achieved through social media content and e-news articles on the SJ Local Food Action Plan, slow food movement, food miles, public transport, local transport projects and initiatives etc.
Promote good public transport
Promote the slow food movement
Promote food miles
Promote resource recycling
7 | Develop and promote land farming, community gardens, community farms, market days, sustainable organic agriculture, the Shire's food bowl, soil sequestration storage, worm farms, green waste to the soil, perennial pastures and community tree planting days. | Medium term | Medium | 2024/25 - 2026/27 | Landcare SJ Inc., Community Development, Switch your thinking, Communications | Number of promotions undertaken | Promote/educate land farming | SYT have promoted the benefits of regenerative agriculture and how community members can help support the movement.
[7 empty] | Promote/educate community gardens | SYT's community workshops and communications, and the Shire's social media and eNewsletters.
[7 empty] | Promote/educate community farms | SYT's community workshops and communications
[7 empty] | Promote/educate market days | SYT's community workshops and communications, and the Shire's weekly promotion of SJ Farmers Market
[7 empty] | Promote/educate sustainable organic agriculture | SYT's community workshops and communications
[7 empty] | Promote/educate Shire's food bowl | Social media and eNewsletters
[7 empty] | Promote/educate soil sequestration storage | SYT's regenerative agriculture promotion.
[7 empty] | Promote/educate worm farms | SYT provide worm farming, composting and bokashi community workshops, and the Shire promotes workshops about reducing waste.
[7 empty] | Promote/educate green waste to the soil | The Shire promotes workshops about reducing waste
[7 empty] | Promote/educate perennial pastures | SYT's regenerative agriculture promotion.
[7 empty] | Promote/educate community tree planting days | Promotion of free verge plant program and Landcare SJ tree planting days. SYT can assist with promotion and are preparing an urban greening community engagement campaign.
8 | Promote behavioural change through a variety of initiatives such as incentives and climage change education programs. | Ongoing | High | 2022/23 - 2029/30 | Switch your thinking, Communications | Behaviour change initiatives developed and delivered | Develop and deliver behaviour change initiatives | Promotion of Swith Your Thinking programs and initiatives via social media and enewsletters
9 | Facilitate increasing levels of community participation in best practice use reduction of water and energy through education and encouragement. | Medium term | High | 2024/25 - 2026/27 | Switch your thinking, Communications | Increased community participation in water and energy efficiency | Educate community on water and energy efficiency | Switch your thinking present a Get Energy Smart at Home workshop about energy efficiency. SJ workshops have been very poorly attended in the last few years despite promoting widely. Communications can assist with promotion through social media and enewsletters. SYT plans to incorporate a water conservation workshop in the new FY.
10 | Increase the Switch your thinking! Rewards for Residents Scheme to reduce emissions. | Ongoing | Medium | 2022/23 - 2029/30 | Switch your thinking, Communications | Increased participation in scheme | Increase participation in Rewards for Residents | This is a consistent and increasing initiative, with promotion assistance by Communications.
11 | Seek partnerships to more accurately estimate and monitor water and energy usage and greenhouse gas emissions in the Shire. | Medium term | Medium | 2024/25 - 2026/27 | Switch your thinking, Facilities | Monitoring of water and energy usage and GHG emissions | Monitor water and energy usage and GHG emissions | SYT have put a case together for SJ to pay for the Azility platform to monitor water and energy usage ($8,500 each after initial set up). Following approval, Facilities staff will be trained in using the software and assist Azility in accessing the appropriate data for the platform.
12 | Integrate fire management practices that maintain levels of public safety while conserving biodiversity, through use and promotion of low flammability plants and fire plans developed for natural areas in consultation with local governments and land managers. | Ongoing | Key | 2022/23 - 2029/30 | Emergency Services, Natural Reserves Coordinator, Landcare SJ Inc. | Integration of fire management practices for both public safety and biodiversity conservation, promotion of low flammability plants, number of natural area fire plans | Integrate fire management practices for both public safety and biodiversity conservation | Natural Reserves and Landcare work closely with Fire and Emergency Services to address community fire risk while considering biodiversity. Emergency Services is engaging with Landcare and the local Winjan Rangers to learn and adopt cultural burning practices that result in fire hazard reduction, stimulation of regrowth of native flora, and attract native fauna.
[7 empty] | Promote low flammability plants | Low flammability plants list is available on the Shire's website. Mitigation Officer is working with local residents and the Natural Reserves Coordinator to encourage planting of native species from the "Keeping it Local" and the DFES "Planting in Asset Protection Zones" Publications.
[7 empty] | Develop fire plans for natural areas | In progress, currently 3 Ecological Fire Management Plans have been completed for Shire managed reserves.
13 | Climate change is expected to favour species that are highly adaptable to change, which are often pest and weed species. Consider the introduction of an adequately funded regional campaign to address new and emerging weed and pest species. | Long term | Key | 2027/28 - 2029/30 | Natural Reserves Coordinator, Landcare SJ Inc., Peel Harvey Biosecurity Group | Scoping paper for management of new and emerging weed and pest species completed | Scoping paper for management of new and emerging weed and pest species | No action - no current resources
14 | Take an inventory of potential direct or indirect offsets, particularly those which could be used in trade for unavoidable clearing which may need to occur. | Long term | Low | 2027/28 - 2029/30 | Natural Reserves Coordinator, Strategic Planning | Scoping paper for offsets completed | Scoping paper for offsets | Various reserves have been considered to be used for offsets now and into the future.
15 | Incorporate new "growing biodiversity and green" technologies and initiatives such as roof, wall gardens and design opportunities to enhance Green Infrastructure as an adaptive response to climate change. | Medium term | Key | 2024/25 - 2026/27 | Parks and Gardens, Engineering Services | Incorporation of green infrastructure by Shire and developers | Incorporate green infrastructure in Shire facilities and new developments | Public Open Spaces in the traditional form still dominate in terms of provision of green space. Other options such as green walls etc will be investigated as opportunity arises.
16 | Plan for larger, more complex and more frequent disasters that cross local government boundaries. | Long term | Key | 2027/28 - 2029/30 | Community Development, Emergency Services | Disaster management plan completed | Disaster management plan for larger, more complex and more frequent disasters | Community Development is involved in the required reviews of the Local Emergency Management Arrangement. The Local Emergency Management Committee (LEMC) is working with the surrounding jurisdictions to foster cooperation and resource sharing in the event of larger more complex disasters. The Shire is involved in the annual testing of Westplan Bushfire which is a regional exercise designed to test response and recovery within the region.
17 | Commit to participation in all waste measuring and reporting requirements. | Short term | High | 2022/23 - 2023/24 | Waste | Participation in waste measuring and reporting programs | Waste measuring and reporting | Completed 20/21 Department of Water & Environment Regulation Waste Audit Data Report, which is completed annually in October.
18 | Maintain the solar hybrid wind turbine to partly power the recreation building in Byford and develop other similar energy and water conservation and efficiency initiatives. | Short term | High | 2022/23 - 2023/24 | Facilities, Switch your thinking | Maintenance of wind turbine, number of Shire facilities with solar panels, number of energy and water efficiency initiatives | Maintain wind turbine on recreation centre | The wind turbine at the SJ Community Recreation Centre was removed several years ago.
[7 empty] | Install solar panels on Shire facilities | 75kw PV Solar System to be installed at Recreation Centre in 22/23. Long term installation program for other facilities to be be developed following completion of Facilities Asset audit.
[7 empty] | Develop energy and water efficiency initiatives | SYT have carried out a Level 2 commercial energy audit at the SJ Community Recreation Centre and are seeking funding to implement recommendations. Facilities monitors energy and water bills monthly, carries out proactive inspections for water leaks and and uses data loggers to monitor water use, displays water efficiency posters and stickers, and uses Smart Approved WaterMarked and Waterwise Approved products and services where possible.
19 | Investigate setting up solar and wind farms in the Shire of Serpentine Jarrahdale. | Long term | Medium | 2027/28 - 2029/30 | Statutory Planning | Scoping paper on solar and wind farms completed | Scoping paper on solar and wind farms | Not commenced as yet.
20 | Consider drafting and introducing a Council Policy on Climate Change and later a possible Climate Change Local Planning Policy. | Short term | High | 2022/23 - 2023/24 | Strategic Planning | Update of Climate Change Strategy and Action Plan completed | Update Climate Change Strategy and Action Plan | Council Policy or Local Planning Policy not the best measure to use. Updated Climate Change Strategy and Local Action Plan drafted.