## SD155.1/06/10

PLANNING SCHEME AMENDMENTS

The following table has been developed at the request of Councillors. The table indicates the progress of current planning scheme amendments (yet to be gazetted).

| **No.** | **Location (Lot)** | **Purpose of Amendment (to be rezoned to)** | **Date**  **Initiated/**  **Adopted by Council** | **EPA**  **Referral** | **EPA**  **Advice Received** | **Advertising Period**  **(42 Days From)** | **Approval by Council** | **Gazettal Date** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 148 | Incorporation of Byford Structure Plan zones into TPS | Textual amendment | 16/08/05 | 30/11/05 | 19/12/05 | 09/12/05 | 27/03/06 |  |
| 150 | Developer Contributions | Textual amendment | 13/04/06  Note:  Amendment Documentation currently being updated to reflect decisions of Council in December 2009. |  |  |  |  |  |
| 151 | Lot 199 Jarrahdale Road, Jarrahdale | Special Residential | 23/07/07  Note: Applicant has not carried out necessary action to progress Amendment 151. |  |  |  |  |  |
| 156 | Lot 1000 (264) Gossage Road, Oldbury | Special Use | 01/08/07  Note: Note: Applicant has not carried out necessary action to progress Amendment 156. |  |  |  |  |  |
| 159 | Lots 81, 210 & 228 Cockram Street & Lots 87 & 88 Mundijong Road and section of the unnamed Road Reserve (south of Cockram Street abutting Lot 81) | Local Reserve – Public Open Space’ to ‘Urban Development’ | Note: Amendment has not progressed as limited staff resources do not permit this at this present time. |  |  |  |  |  |
| 160 | Lot 5 #1409 Karnup Road Serpentine | Rural to Farmlet | 18/08/08 | 05/06/09 | 30/06/09 | 30/07/09 | 26/10/09 |  |
| 161 | Lot 128, Lot 3 South Western Highway and Lot 1 Pinebrook Road, Byford | Rural to Urban Development consistent with Urban zoning under MRS | 16/09/08 | 06/11/08 | 06/04/09 | 21/05/09 | 24/08/09 | 25/05/10 |
| 162 | Serpentine Structure Plan area | Serpentine Structure Plan area | 18/09/08 | 20/05/09 | 15/06/09 | 04/08/09 |  |  |
| 164 | Integration of the Byford Townsite Drainage and Water Management Plan | N/A | 25/05/09 | 08/09/09 | 30/09/09 | 05/11/09 | 22/02/10 |  |
| 165 | Rural Lot Creation | Textual Amendment | 30/06/09 | 08/09/09 | 30/09/09 | 19/01/10 |  |  |
| 166 | Lot 782 Walker Road, Serpentine | Rural to Farmlet |  |  |  |  |  |  |